## Cover Page
AEON Microfinance Cambodia Credit Card System Project Status Report
Document Details
Created/Updated By | Create/Update Date | Reviewed/Approved By | Review/Approve Date
Jhoycee Cruz | 2013-10-29

## Status
Project Monitoring |  | Project Name |  | ACSPH Credit Card System |  |  |  | Updated By |  |  | J. Cruz
|  | Document Category: |  | Status |  |  |  | Updated Date |  |  | 2013-10-28
Tasks Completed
Task / Activity | Task Category |  | Action Plan |  | Person In Charge | Start Date | End Date |  | Progress | Remarks
Finalization of Project Schedule | Project Planning |  | Submit to ACSKH Team |  | J. Cruz | 2013-09-27 | 2013-09-30 |  | 100% | Please refer to High Level Schedule Sheet
Submit Questionnaire v 1.01 | Requirements Gathering |  | Submit Document to Client |  | J. Alabat K. Labustro E. Lanorio | 2013-09-19 | 2013-10-14 |  | 100% | 10/23: Submitted to ACSKH Team for Feedback 10/28: Waiting for ACSKH's confirmation
AS400 Hardware Specs Finalization | Project Planning |  | Finalize needed specifications |  | J. Alabat | 2013-09-19 | 10/5/2013 10/25/2013 |  | 100% | 10/25: Final Proposal already approved by Sir Jerome and forwarded to ACSKH Team
Tasks In-Progress
Task / Activity | Task Category |  | Action Plan |  | Person In Charge | Start Date | End Date |  | Progress | Remarks
Submit Hardware and Software Configuration | Project Planning |  | Submit Document to Client |  | W. Santoalla/ J. Cruz | 2013-09-19 | 09/25/2013 10/28/2013 |  | 50% | In Progress
FEP Hardware Specs Finalization | Project Planning |  | Finalize needed specifications |  | K. Labustro | 2013-09-19 | 10/5/2013 10/25/2013 10/30/2013 |  | 80% | In Progress [FEP - 20131025] Recommendation has been sent to Sales team. Sales team is requesting results of performance testing using 2-core in VM environment. FEP team will provide results on 10/30.
Network Diagram and Configuration | Project Planning |  | Create proposal for client |  | W. Santoalla | 2013-09-19 | 10/5/2013 10/25/2013 |  | 50% | In Progress
MC and VISA Application | Planning |  | Submit Application to VISA and MasterCard |  | ACSKH/ J. Cruz | ASAP |  |  |  | 10/25: Request for ACSKH's PIC sent to Mr. Vannak
Creation of Requirement Definition Document | Requirement Gathering |  | Submit Document to Client |  | J. Cruz | 2013-10-17 | 2013-11-06 |  | 50% | In Progress ** Dependent on Client's answers on Questionnaires
Table and Interface Mapping | Requirement |  | Finalize needed specifications |  | J. Lanorio | 2013-10-17 | 2013-10-29 |  | 50% | In Progress
Set-up of FEP Development and Verification Servers | Construction |  | Handover to Infra team for complete FEP set-up. |  | FEP team | 2013-10-21 | 2013-10-31 |  | 20% | In Progress
Tasks Not Yet Started
Task / Activity | Task Category |  | Action Plan |  | Person In Charge | Start Date | End Date |  | Progress | Remarks
Analysis and Design (BD and DD Design Creation) | Design |  | Complete Design of affected modules to align with the requirements |  | ACSS Team |  |  |  |  | [FEP 10/28] Dependency: To finalize the design, answers in the questionairre is needed.
System Construction and Unit Testing | Development |  | Development the System Requirement based on design |  | ACSS Team |  |  |  |  | [FEP 10/28] System Construction has started last 10/21.
System Testing ( Offsite - Functional Testing ) | Testing |  | Perform end to end sytem testing based on available offsite infrastructure. Exclude testing with Card Brand |  | ACSS Team
Connectivity Testing Onsite (Prod and DR Servers) | Testing |  | Perform connectivity testing of Production and DR Servers environment |  | ACSS Team
System Integration Testing (Onsite - DR Servers) | Testing |  | System Integration Testing among HW/SW products (FAX, Email, AFIS, Credit Card, FEP, HSM, PIN Mailer, Billing, etc) excluding Card Brand |  | ACSS Team
User's Training & UAT (PROD) | Testing |  | Conduct User Training and System User Acceptance testing (Functional) |  | ACSS/ ACSKH
Certification Activities (DR) | Testing |  | System Integration Testing with Card Brand |  | ACSS/ ACSKH
Pre-Cut Over Activities (Prod and DR) | Implementation |  | Once Pass end to end Testing. Clean up of Test Data on the Production and DR Environment |  | ACSS Team
System Delivery (Launching) | Implementation |  | Go Live. |  | ACSS/ ACSKH

## High Level Schedule
Project Monitoring |  |  |  |  | Project Name | [12 empty] | ACSKH Credit Card System | [12 empty] | Created/Updated By | [12 empty] | J. Cruz
[5 empty] | Document Category: | [12 empty] | High Level Schedule | [12 empty] | Created/Updated Date | [12 empty] | 2013-09-24
ACSKH - Credit Card System Project High-Level Schedule | [31 empty] | 2014
SEQ | Project Phase | Environment | PIC | Original Date | % Complete | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | May
Reschedule
|  |  |  | Actual Date |  | w1 | w2 | w3 | w4 | w5 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w5 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w5 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w5 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4 | w1 | w2 | w3 | w4
1 | Project Kick Off Meeting |  | ACSS ACSKH | 2013-07-01 | bar: w1
|  |  |  | 2013-07-02 | 100%
2 | Meeting in Cambodia |  | ACSS ACSKH | 9/23 - 09/27 | bar: w4
3 | Requirements Gathering (FRS and BPF Development) |  | ACSS/ ACSKH | 07/01 - 09/27 | bar: w2 to w4
ACSS/ACSPh | bar: w2 to w4
4 | Design final configuration/quotation |  | ACSS/ ACSKH | 10/01 - 10/18 | bar: w1 to w3
ACSS/ACSPh | bar: w1 to w4
5 | Hardware Order |  | ACSS/ ACSKH | 10/21 - 10/25 | bar: w4
ACSS/ACSPh
6 | FEP Hardware Delivery and Set Up to Bangkok | AS400/FEP | ACSS - FJ | 10/28 - 11/29 12/02 - 12/13 | bar: w5 to w2
ACSS/VENDOR
7 | FEP Hardware Delivery to Cambodia | AS400/FEP | ACSS - FJ | 12/16 - 12/27 | bar: w3 to w4
ACSS/VENDOR
8 | HOST Hardware Delivery to Cambodia | AS400/FEP | ACSS - HOST VENDOR
ACSS/VENDOR
9 | AFIS Hardware Delivery to Cambodia | AS400/FEP | ACSS- AFIS VENDOR
ACSS/VENDOR
10 | FEP KT to SI Group | AS400/FEP | ACSS - FJ | 12/30 - 01/09 | bar: w1 to w2
ACSS/VENDOR
11 | FEP Middleware Installation | AS400/FEP | ACSS -FEP | 01/13 - 01/31 | bar: w3 to w5
ACSS/VENDOR
12 | AFIS Middleware Installation and Final Set Up | AS400/FEP | ACSS- AFIS VENDOR
ACSS/VENDOR
13 | HOST Middleware Installation and Final Set Up | AS400/FEP | ACSS - HOST VENDOR
ACSS/VENDOR
14 | Analysis and Design (BD and DD Design Creation) | AS400/FEP | ACSS Team | 09/09 - 10/18 | bar: w2 to w3
a. FEP
b. HOST
| c. AFS |  | ACSS/VENDOR
15 | System Construction and Unit Testing | AS400/FEP | ACSS Team | 09/23 - 11/29 | bar: w4 to w4
a. FEP
b. HOST
| c. AFS |  | ACSS/VENDOR
16 | System Testing ( Offsite - Functional Testing ) | AS400/FEP | ACSS Team | 10/28 - 01/31 | bar: w5 to w5
a. FEP - HOST
| b. HOST - AFS |  | ACSS/VENDOR
17 | Connectivity Testing Onsite (Prod and DR Servers) | AS400/FEP | ACSS Team | 02/03 - 02/21 | bar: w1 to w3
a. FEP
b. HOST
| c. AFS |  | ACSS/VENDOR
18 | System Integration Testing (Onsite - DR Servers) | AS400/FEP | ACSS Team | 02/24 - 03/14 | bar: w4 to w2
a. FEP - HOST
| b. HOST - AFS |  | ACSS/VENDOR
19 | Non Functional System Testing ( Onsite - PROD Servers) | Onsite PROD Server | ACSS Team | 02/24 - 03/14 | bar: w4 to w2
| System Testing ( Non Functional Testing - PROD) |  | ACSS
20 | User's Training & UAT (PROD) | Onsite PROD Server | ACSS/ ACSKH | 02/24 - 04/18 | bar: w4 to w3
| User's Training & UAT (VER) |  | ACSS/ACSPh
21 | MC and VISA Application | Onsite DR Server | ACSS/ ACSKH | 10/01 - 03/14 | bar: w1 to w2
| Certification Activities (DR) |  | ACSS/Client
22 | Certification Activities (DR) | Onsite DR Server | ACSS/ ACSKH | 03/17 - 04/25 | bar: w3 to w4
| Certification Activities (DR) |  | ACSS/Client
23 | Pre-Cut Over Activities (Prod and DR) | Onsite Prod and DR Server | ACSS | 04/24 - 05/02 | bar: w4 to w5; w1
| Pre-Cut Over Activities |  | ACSS
24 | System Delivery (Launching) | Onsite Prod and DR Server | ACSS/ ACSKH | 05/05 - 05/09 | bar: w2
| System Delivery (Launching) |  | ACSS/ACSPh
With FJ Schedule Consideration

## AS400 HW & SW Configuration
Project Monitoring |  | Project Name | ACSKH Credit Card System | Created/Updated By | Jerome Alabat
|  | Document Category | Hardware & Software Configuration | Create / Update Date | 2013-09-30
ISERIES Proposal Comparison
|  | Option 2 - Prod Box | Option 2 - DR Box (with 2 logical partitions)
| System Type & Model | 8202-E4D | 8202-E4D
| Processor | 3.6 Ghz Power7+ | 3.6 Ghz Power7+
| No. of Cores | 6-core (1-core License) | 6-core (1-core License)
CPW
| Client/Server Env't. | 7066.6667 | 7066.6667
| Interactive Env't. | 7066.6667 | 7066.6667
| Memory (MB) |  | 32768
| Total | 32768
| Disk (GB) : | (1668 GB hard disk or
| Total Disks | 139GB 15k RPM SAS SFF‐2 Disk Drive (IBM i) x 12 ) | (1668 GB hard disk) | (1668 GB hard disk)
| Effective | to be determined | to be determined | to be determined
| Media Device |  |  | -
| Internal | SATA Slimline DVD-RAM Drive | SATA Slimline DVD-RAM Drive
DVD-RAM SATA/SAS Sled
| External | HHLTO6 SAS Tape Drive | HHLTO6 SAS Tape Drive
| Rack | 7014-T42 | 7014-T42
| System Console | 7042-CR7 Rack-mounted Hardw.Mgmt.Console | 7042-CR7 Rack-mounted Hardw.Mgmt.Console
| LAN |  |  | 1 x 2-Port 10/100/1000 Base-TX Ethernet
| Ethernet | 2 x PCIe2 4-port 1GbE Adapter | 2 x PCIe2 4-port 1GbE Adapter
| Processor Group | P10 | P10
| Software Version | Version 6 Release 1.1 | Version 6 Release 1.1
| Software List | 5761-PT1 IBM Performance Tools for i5/OS | 5761-PT1 IBM Performance Tools for i5/OS | 5761-PT1 IBM Performance Tools for i5/OS
|  | 5761-QU1 IBM Query for i5/OS | 5761-QU1 IBM Query for i5/OS | 5761-QU1 IBM Query for i5/OS
|  | 5761-SS1 IBM i V6 | 5761-SS1 IBM i V6 | 5761-SS1 IBM i V6
|  | 5761-SSA IBM i per Processor License Billing (1-core) | 5761-SSA IBM i per Processor License Billing (1-core) | 5761-SSA IBM i per Processor License Billing (1-core)
|  | 5761-SSC IBM i per User Billing (Unlimited) | 5761-SSC IBM i per User Billing (Unlimited) | 5761-SSC IBM i per User Billing (Unlimited)
|  | 5761-ST1 IBM DB2 Query Manager and SQL Dev Kit for IBM i | 5761-ST1 IBM DB2 Query Manager and SQL Dev Kit for IBM i | 5761-ST1 IBM DB2 Query Manager and SQL Dev Kit for IBM i
|  | 5761-WDS IBM WebSphere Development Studio | 5761-WDS IBM WebSphere Development Studio | 5761-WDS IBM WebSphere Development Studio
|  | ILE Compiler License Registration (3) | ILE Compiler License Registration (3) | ILE Compiler License Registration (3)
|  | Appl Dev ToolSet License Registration (3) | Appl Dev ToolSet License Registration (3) | Appl Dev ToolSet License Registration (3)
|  | 5761-XW1 System i Access Family | 5761-XW1 System i Access Family | 5761-XW1 System i Access Family
|  | 5765-EXP IBM Systems Director Express Edition for | 5765-EXP IBM Systems Director Express Edition for | 5765-EXP IBM Systems Director Express Edition for
|  | 5765-PVS PowerVM Standard Edition | 5765-PVS PowerVM Standard Edition | 5765-PVS PowerVM Standard Edition
|  | 5773-PVS PowerVM Standard Edition SW Maintenance: 3Yrs | 5773-PVS PowerVM Standard Edition SW Maintenance: 3Yrs | 5773-PVS PowerVM Standard Edition SW Maintenance: 3Yrs
|  | 5733-QU2 IBM DB2 Web Query for i Option Base | 5733-QU2 IBM DB2 Web Query for i Option Base
|  | 5761-JV1 IBM Developer Kit for Java | 5761-JV1 IBM Developer Kit for Java
|  | 5761-DG1 IBM HTTP Server for i5/OS | 5761-DG1 IBM HTTP Server for i5/OS
|  | 5761-TC1 TCP/IP Connectivity Utilities for i5/OS | 5761-TC1 TCP/IP Connectivity Utilities for i5/OS
|  | 5761-XE1 System i Access for Windows | 5761-XE1 System i Access for Windows
|  | 5662-EXP IBM Systems Director Express Edition for IBM i | 5662-EXP IBM Systems Director Express Edition for IBM i
|  | 5662-WQE 3-Year Registration for 5733-WQE | 5662-WQE 3-Year Registration for 5733-WQE
|  | 5692-A6P System Software | 5692-A6P System Software
|  | 5722-WE2 Web Enablement for i5/OS | 5722-WE2 Web Enablement for i5/OS
|  | 5733-ARE IBM Application Runtime Expert for i | 5733-ARE IBM Application Runtime Expert for i
|  | 5733-SP3 IBM Software Maintenance for IBM i and Selected products | 5733-SP3 IBM Software Maintenance for IBM i and Selected products
|  | 5733-SPE IBM Software Maintenance for IBM i and Selected products | 5733-SPE IBM Software Maintenance for IBM i and Selected products | 5733-SPE IBM Software Maintenance for IBM i and Selected products
|  | 5733-WQE IBM Web Query for System i Express | 5733-WQE IBM Web Query for System i Express | 5733-WQE IBM Web Query for System i Express
|  | 5733-WQX IBM Web Query for System i Registration | 5733-WQX IBM Web Query for System i Registration | 5733-WQX IBM Web Query for System i Registration
|  | 5761-AMT IBM Rational Application Management Tool | 5761-AMT IBM Rational Application Management Tool | 5761-AMT IBM Rational Application Management Tool
| TOTAL PRICE |  | ?
| TOTAL PRICE W/ VAT | total = USD $667,986 | ?

## Issues
Project Monitoring |  |  | Project Name |  |  | ACSKH Credit Card System |  | Updated By |  |  | K. Labustro
|  |  | Document Category: |  |  | Issues |  | Updated Date |  |  | 2013-10-22
Summary of Issues Encountered
Issue # | Description | By |  | Category | Severity | Recommendations / Required Action | To |  | Status | Date |  | Action Taken
1 | Availability of Servers | ACSS |  | Procurement | Critical | Servers should be procured, November at the latest | ACSKH |  | In Progress |  |  | [FEP 10/28] Final Quotation is under discussion with Sales team, Client and Fujitsu Thailand.
2 | Requirements Gathering | ACSS |  | Requirements Gathering | High | All teams should start with the Requirements gathering processes as the schedule is now running | ACSKH |  | In Progress |  |  | 10/28: ACSS team is requesting for follow-up email regarding answers to questionnaire file from client.
3 | Schedule Confirmation | ACSS |  | Planning | High | Not Yet Finalized | ACSKH |  | In Progress
4 | Availability of Data Center | ACSK |  | Planning | High | Coordinate with ACSKH | ACSKH |  | Not Yet Started
5 | Finalization of FEP Servers Spec | ACSS |  | Planning | High | Need to have review meeting with project team to finalize recommendations sent by Fujitsu Thailand sent 10/22 | ACSKH |  | In Progress |  |  | The review meeting did not commenced as planned. As of 10/23, FEP team sent the recommendations based on FEP performance testing given the CPU core, storage and memory requirement in other ACS (currently LIVE). Action item: Waiting for confirmation from sales team/client regarding on final quotation.

## Risk
Project Monitoring |  |  | Project Name |  |  | ACSKH Credit Card System |  | Updated By |  | E. Lanorio
|  |  | Document Category: |  |  | Risk |  | Updated Date |  | 2013-10-18
Summary of Risks
1 | Risk | Risk Category |  | Risk Trigger | Potential Outcome |  | Raised By | Date Raised | Priority | Risk Impact
| Confirmation of Data Center to be used | High |  | If DC is not determined by November | Schedule will be delayed |  | J. Cruz | 2013-10-04 | High | Schedule will be delayed
| Probability | Risk Strategy |  | MITIGATION | Risk Owner |  | Status | Status Date | Action Taken
| High |  |  | Follow up with Client for DC Finalization | ACSKH |  | Not Yet Started | 2013-10-04 | None Yet
2 | Risk | Risk Category |  | Risk Trigger | Potential Outcome |  | Raised By | Date Raised | Priority | Risk Impact
| Application to Card Brands Membership | High |  | if Application is not started by November | Certification and Launch Schedule will be delayed. |  | J. Cruz / K. Labustro | 2013-10-14 | High | Schedule will be delayed
| Probability | Risk Strategy |  | MITIGATION | Risk Owner |  | Status | Status Date | Action Taken
| High | FOLLOW-UP |  | Follow Up with Client for Card Brand Application | ACSKH |  | Not Yet Started | 2013-10-29 | [FEP 10/29] Need to send a follow-up email for status of application. Cc FEP PM on this email follow-up.
3 | Risk | Risk Category |  | Risk Trigger | Potential Outcome |  | Raised By | Date Raised | Priority | Risk Impact
| No Credit Card Application Form provided by the client | High |  | Application Form should be provided by Oct 25 | RD Will not be finalize |  | J. Lanorio | 2013-10-18 | High | Development will be delay
| Probability | Risk Strategy |  | MITIGATION | Risk Owner |  | Status | Status Date | Action Taken
| High |  |  | Follow up with Client | ACSKH |  | None yet
4 | Risk | Risk Category |  | Risk Trigger | Potential Outcome |  | Raised By | Date Raised | Priority | Risk Impact
| CBC Connectivity and XSD | High |  | Client should provide the information before the start of Development by November 8 | Development will be delayed |  | J. Lanorio | 2013-10-18 | High | Development will be delay
| Probability | Risk Strategy |  | MITIGATION | Risk Owner |  | Status | Status Date | Action Taken
5 | Risk | Risk Category |  | Risk Trigger | Potential Outcome |  | Raised By | Date Raised | Priority | Risk Impact
| Probability | Risk Strategy |  | MITIGATION | Risk Owner |  | Status | Status Date | Action Taken

## Completed Tasks
Project Monitoring |  |  | Project Name |  | ACSKH Credit Card System |  |  |  | Updated By |  |  | J. Cruz
|  |  | Document Category: |  | Completed Tasks |  |  |  | Updated Date |  |  | 2013-10-28
COMPLETED TASKS
No | Tasks/ Activity | Task Category |  | Action Plan |  | Person In Charge | Start Date | End Date |  | Progress | Remarks Issues/ Concerns
1 | Finalization of Project Schedule | Project Planning |  | Submitted to ACSKH Team |  | J. Cruz | 2013-09-27 | 2013-09-30 |  | 100% | not yet approved by client
2 | Submission of Questionnaire | Requirements Gathering |  | Submitted to ACSKH Team |  | J. Cruz | 2013-09-19 | 2013-10-14 |  | 100% | feedback from client received on 10/15/2013
3 | AS400 Hardware Specs Finalization | Project Planning |  | Submitted to ACSKH Team. Procurement to be Started |  | J. Alabat | 2013-09-23 | 2013-10-25 |  | 100% | Actual Procurement not yet started
4 | Submission of Questionnaire | Requirements Gathering |  | Submitted to ACSKH Team |  | J. Cruz | 2013-10-15 | 2013-10-23 |  | 100% | feedback from client received 10/28/2013

## Cambodia Holidays
Project Monitoring | [14 empty] | Project Name | [15 empty] | ACSKH Credit Card System | [5 empty] | Updated By
[15 empty] | Document Category: | [15 empty] | Philippine Holidays | [5 empty] | Updated Date
Philippines List of Holiday for 2013
Item No | Holiday Name | [21 empty] | Date | [12 empty] | Comment
1 | International New Year’s Day | [21 empty] | 2013-01-01
2 | Victory Over Genocide Day | [21 empty] | 2013-01-07
3 | International Women's Day | [21 empty] | 2013-03-08
4 | Meak Bochea Day /Magha Puja Day | [21 empty] | 2013-03-27
5 | Cambodian Khmer New Year/Chaul Chnam Thmey | [21 empty] | April 14-16, 2013
6 | Labor Day | [21 empty] | 2013-05-01
7 | Royal Ploughing Ceremony | [21 empty] | 2013-05-11
8 | King Sihamoni’s Birthday | [21 empty] | May 13-15, 2013
9 | Visaka Bochea Day | [21 empty] | 2013-05-25
10 | Queen Mother's Birthday | [21 empty] | 2013-06-18
11 | Constitution Day | [21 empty] | 2013-09-24 | 41541 | 41541 | 41541 | 41541 | 41541 | 41541 | 41541 | 41541 | 41541 | 41541 | 41541 | 41541
12 | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | 2013-10-03 | 41550 | 41550 | 41550 | 41550 | 41550 | 41550 | 41550 | 41550 | 41550 | 41550 | 41550 | 41550
13 | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | 2013-10-04 | 41551 | 41551 | 41551 | 41551 | 41551 | 41551 | 41551 | 41551 | 41551 | 41551 | 41551 | 41551
14 | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | Pchum Ben Festival | 2013-10-14 | 41561 | 41561 | 41561 | 41561 | 41561 | 41561 | 41561 | 41561 | 41561 | 41561 | 41561 | 41561
15 | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | 2013-10-28 | 41575 | 41575 | 41575 | 41575 | 41575 | 41575 | 41575 | 41575 | 41575 | 41575 | 41575 | 41575
16 | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | Company Outing | 2013-10-29 | 41576 | 41576 | 41576 | 41576 | 41576 | 41576 | 41576 | 41576 | 41576 | 41576 | 41576 | 41576
17 | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | King Father’s Birthday | 2013-10-31 | 41578 | 41578 | 41578 | 41578 | 41578 | 41578 | 41578 | 41578 | 41578 | 41578 | 41578 | 41578
18 | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | Independence Day | 2013-11-09 | 41587 | 41587 | 41587 | 41587 | 41587 | 41587 | 41587 | 41587 | 41587 | 41587 | 41587 | 41587
19 | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | Water Festival | 2013-11-27 | 41605 | 41605 | 41605 | 41605 | 41605 | 41605 | 41605 | 41605 | 41605 | 41605 | 41605 | 41605
20 | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | Human Rights Day | 2013-12-10 | 41618 | 41618 | 41618 | 41618 | 41618 | 41618 | 41618 | 41618 | 41618 | 41618 | 41618 | 41618
21